## Gantt Chart
	M12 Final project				0%
	W.W.C.A
			13/02/22

										07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Feb-22					Mar-22					Apr-22					May-22					Jun-22					Jul-22					Aug-22
			14-Feb-2022	32	29-Mar-2022	0%	44			14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13
		Roger Puga Ruiz	14-Feb-2022	32	29-Mar-2022	0%	44	10	7
	1	See the historical pollution map	14-Feb-2022	7	22-Feb-2022	0%	9	0	7
	2	Login, Logout and register	23-Feb-2022	10	08-Mar-2022	0%	14	0	10
	3	Show News	09-Mar-2022	4	14-Mar-2022	0%	6	0	4
	4	See relevants news	15-Mar-2022	4	18-Mar-2022	0%	4	0	4
	5	Validate User	19-Mar-2022	4	23-Mar-2022	0%	5	0	4
	6	Authenticate User	24-Mar-2022	4	29-Mar-2022	0%	6	0	4

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		01/01/14
		04/03/14
		18/04/14
		20/04/14
		25/04/14
		01/05/14
		10/06/14
		15/08/14
		08/12/14
		25/12/14