## Gantt Chart
	M12 Final project				74%
	W.W.C.A
			27/05/22

										17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41					42
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	abr-22					may-22					jun-22					jul-22					ago-22					sep-22					oct-22
			25-abr-2022	17	17-may-2022	74%	23			25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22
		Iván de Monserrat Navarro	25-abr-2022	17	17-may-2022	100%	23	5	0
	1	Create dataBase	25-abr-2022	1	25-abr-2022	100%	1	1	0
	2	Receive information from weather stations / Get API data	25-abr-2022	4	28-abr-2022	100%	4	4	0
	3	Validate information from API and get most relevant info	28-abr-2022	2	29-abr-2022	100%	2	2	0
	4	Insert data into dataBase	29-abr-2022	3	03-may-2022	100%
	5	Create backend server + Configuration	03-may-2022	4	06-may-2022	100%
	6	Create spain Map on D3 with angular	06-may-2022	5	12-may-2022	0%
	7	Create backend functions for request data to dataBase	12-may-2022	3	16-may-2022	50%
	8	D3 map station points	16-may-2022	2	17-may-2022	0%
	9	D3 map zoom	17-may-2022	1	17-may-2022	0%
	10	Show ranking	17-may-2022	2	18-may-2022	0%
	11	Show info data	18-may-2022	2
	12	Show forecast data	30-dic-1899	2
	13	Show additional info	30-dic-1899	1

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays