## Gantt Chart
	M12 Final project				0%
	W.W.C.A
			17/02/22

										09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	feb-22		mar-22					abr-22					may-22					jun-22					jul-22					ago-22
			27-feb-2022	44	14-abr-2022	0%	47			27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
		Albert Casany Vila	27-feb-2022	44	14-abr-2022	0%	47	0	17
	1	Create a new user	27-feb-2022	7	07-mar-2022	0%	9	0	7
	2	Delete news	28-feb-2022	10	11-mar-2022	0%	12	0	10
	3	Read users	12-mar-2022	9	23-mar-2022	0%	12	0	9
	4	Delete users	24-mar-2022	8	04-abr-2022	0%	12	0	8
	5	Update users	05-abr-2022	3	07-abr-2022	0%	3	0	3
	6	Change the configuration page	07-abr-2022	6	14-abr-2022	0%	8	0	6

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/01/14
		4/03/14
		18/04/14
		20/04/14
		25/04/14
		1/05/14
		10/06/14
		15/08/14
		8/12/14
		25/12/14