## Gantt Chart
	M12 Final project				72%
	W.W.C.A
			05/27/22

										17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Apr-22					May-22					Jun-22					Jul-22					Aug-22					Sep-22					Oct-22
			19-Apr-2022	25	24-May-2022	72%	36			19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16
		Roger Puga Ruiz	19-Apr-2022	25	24-May-2022	100%	36	9	0
	1	Authenticate users	19-Apr-2022	7	27-Apr-2022	100%	9	7	0
	2	Authorize users	27-Apr-2022	2	28-Apr-2022	100%	2	2	0
	3	Users can update their profile.	28-Apr-2022	2	29-Apr-2022	100%	2	2	0
	4	Users can message other users (websockets)	29-Apr-2022	5	05-May-2022	100%
	5	Admins can manage the users (CRUD)	05-May-2022	2	09-May-2022	100%
	6	Admins can view the page statistics	09-May-2022	6	16-May-2022	0%
	7	Researchers can write news	16-May-2022	3	18-May-2022	50%
	8	Users can interact with the forums	18-May-2022	2	19-May-2022	0%
	9	Users can view and comment news	19-May-2022	4	24-May-2022	0%
	10	Users can change their password. Includes e-mail verification.	24-May-2022	4	27-May-2022	0%

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/1/14
		3/4/14
		4/18/14
		4/20/14
		4/25/14
		5/1/14
		6/10/14
		8/15/14
		12/8/14
		12/25/14
		5/6/22