## Gantt Chart
	M12 Final project				95%
	W.W.C.A
			26/05/22

										17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41					42
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	abr-22					may-22					jun-22					jul-22					ago-22					sep-22					oct-22
			25-abr-2022	44	25-may-2022	95%	31			25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22
		Albert Casany Vila	25-abr-2022	44	25-may-2022	99%	31	11	1
	1	Create a map	25-abr-2022	10	06-may-2022	100%	12	10	0
	2	Clean csv	06-may-2022	2	09-may-2022	95%	4	1	1
	3	information when you hover your mouse over it	09-may-2022	2	10-may-2022	90%	2	1	1
	4	Flask Backend	11-may-2022	4	16-may-2022	40%	6	1	3
	5	Statistics bar chart Agriculture d3	17-may-2022	5	23-may-2022	95%	7	4	1
	6	interactive slider for each year	24-may-2022	2	25-may-2022	100%	2	2	0
	7	Style page	25-may-2022	2	26-may-2022	90%	2	1	1

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/01/14
		4/03/14
		18/04/14
		20/04/14
		25/04/14
		1/05/14
		10/06/14
		15/08/14
		8/12/14
		25/12/14