## Gantt Chart
	M12 Final project				99%
	W.W.C.A
			27/05/22

										17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41					42
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	abr-22					may-22					jun-22					jul-22					ago-22					sep-22					oct-22
			25-abr-2022	20	20-may-2022	99%	26			25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22
		Iván de Monserrat Navarro	25-abr-2022	20	20-may-2022	100%	26	5	0
	1	Create dataBase	25-abr-2022	1	25-abr-2022	100%	1	1	0
	2	Receive information from weather stations / Get API data	25-abr-2022	4	28-abr-2022	100%	4	4	0
	3	Validate information from API and get most relevant info	28-abr-2022	2	29-abr-2022	95%	2	1	1
	4	Insert data into dataBase	29-abr-2022	4	04-may-2022	100%	6	4	0
	5	Create backend server + Configuration	04-may-2022	5	10-may-2022	90%	7	4	1
	6	Create spain Map on D3 with angular	10-may-2022	6	17-may-2022	100%	8	5	1
	7	Create backend functions for request data to dataBase	17-may-2022	3	19-may-2022	100%	3	3	0
	8	D3 map station points	19-may-2022	2	20-may-2022	100%	2	2	0
	9	D3 map zoom	20-may-2022	1	20-may-2022	100%	1	1	0
	10	Show ranking	20-may-2022	2	23-may-2022	100%	4	2	0
	11	Show info data	23-may-2022	3	25-may-2022	100%	3	3	0
	12	Show forecast data	25-may-2022	2	26-may-2022	100%	2	2	0
	13	Show additional info	26-may-2022	2	27-may-2022	80%	2	1	1

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays