## requirement lists
Instructions:
1. Write your team name, full names and project hours instead of «Student X (xx hours)».
2. Write as many functional requirements as you see fit.
3. Keep the current format.
4. Keep it all in a single spreadsheet.
5. Paste these lists in the main document (.odt)
6. Submit this file (.ods) together with the main document (.odt)

Team name:	World With Clear Air (W.W.C.A)

Roger Puga Ruiz (66h)
ID	Functional Requirements	Workload		Priority
FR1	Authenticate users	1
FR2	Authorize users	1
FR3	Users can update their profile.	0,5
FR4	Users can change their password. Includes e-mail verification.	1
FR5	Users can view and comment news	1	?	4
FR6	Users can message other users (websockets)	1,3	+2 DAYS	1
FR7	Admins can manage the users (CRUD)	0,2
FR8	Admins can view the page statistics	1	+2 DAYS	5	(Visitas y logins)
FR9	Researchers can write news	1	?	3
FR10	Users can interact with the forums	0,5	(Varios foros)	6
FR11	Users can view and comment on images of molecules.	1		2
FR12	Query NCBI about molecules (call Python)	0,5		7
Total:		10

Iván de Montserrat
ID	Functional Requirements	Workload
FR7	Comment News	1,5
FR8	Report wrong news	2
FR9	Read and write message	3
FR10	Create News	1,5
FR11	Comment News	2
...
...
...
Total:		10

Albert Casany
ID	Functional Requirements	Workload
FR12	Create map d3	2,5
FR13	information when you hover your mouse over it	1,5
FR14	Clean CSV	0,5
FR15	Flask Backend	1,5
FR16	Statistics bar chart Agriculture d3	2
FR17	interactive slider for each year	1,5
FR18	Styles page	0,5
...
Total:		10

## test example
FR2: create_doctor(String: dni) → Doctor
1. Must throw an exception if DNI does not match pattern "8 digits + 1 letter".
2. Must throw an exception if DNI is already in database.
3. Must return a Doctor object with the same dni upon success.
4. After creating the doctor, read_doctor(dni) must return a doctor object with the same dni.